## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US001 | As a developer, I want to paste an error/stack trace so it is saved as a bug record. | Must | - | Amrutha | Done
1 | 1 | US002 | As a developer, I want to upload a log/text file as a bug report. | Must Have | US001 | Amrutha | Done
1 | 1 | US003 | As a developer, I want submissions validated (file type, size, empty content) before saving. | Must | US002 | Amrutha | Done
1 | 1 | US004 | As a developer, I want each bug to get a unique, human-readable . | Must | US001 | Amrutha | Done
1 | 1 | US005 | As a developer, I want to see a live preview of the detected error type while typing/uploading. | Should | US001 | Amrutha | Done
2 | 2 | US006 | As a developer, I want to view a history list of all my past bug submissions. | Must | US004 | Amrutha | Done
2 | 2 | US007 | As a developer, I want to open a submission and see its full stored content and metadata. | Must | US006 | Amrutha | Done
2 | 2 | US008 | As a developer, I want to delete a bug submission I no longer need. | Could | US006 | Amrutha | Done
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 120 | 10 | 12 | 12 | 11 | 12 | 8 | 12 | 7 | 4 | 6 | 4 | 6 | 5 | 11
SPRINT 1 BACKLOG
US001 | T01 | Configure backend framework and dependencies | 06-Jul-2026 | 07-Jul-2026 | Amrutha | Development | Done | 6 | Day 1: 6
US001 | T02 | Design Bug Submission page UI | 07-Jul-2026 | 07-Jul-2026 | Amrutha | UI Design | Done | 5 | Day 2: 5
US001 | T03 | Develop bug report upload API | 07-Jul-2026 | 08-Jul-2026 | Amrutha | Backend Development | Done | 8 | Day 3: 8
US001 | T04 | Implement file validation (extension, size, empty-content checks) | 08-Jul-2026 | 08-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 4: 6
US001 | T05 | Design database schema for bug reports | 08-Jul-2026 | 09-Jul-2026 | Amrutha | Database Design | Done | 7 | Day 5: 7
US001 | T06 | Store uploaded bug reports in database | 09-Jul-2026 | 09-Jul-2026 | Amrutha | Backend Development | Done | 5 | Day 6: 5
US001 | T07 | Implement upload success/error messages | 09-Jul-2026 | 10-Jul-2026 | Amrutha | Frontend Development | Done | 6 | Day 7: 6
US009 | T08 | Design Triage Agent rules: severity keyword sets, weighting logic, and confidence scoring approach | 14-Jul-2026 | 14-Jul-2026 | Amrutha | Design | Done | 4 | Day 1: 4
US009 | T09 | Implement TriageAgent.classify() — severity scoring and Medium default fallback for weak signals | 15-Jul-2026 | 15-Jul-2026 | Amrutha | Backend Development | Done | 7 | Day 2: 7
US009 | T10 | Implement priority mapping (P0-P3) and urgency-keyword priority bump logic | 16-Jul-2026 | 16-Jul-2026 | Amrutha | Backend Development | Done | 4 | Day 3: 4
US009 | T11 | Implement component classification (Auth, Payments, DB, API, Frontend, etc.) via keyword scoring | 17-Jul-2026 | 17-Jul-2026 | Amrutha | Backend Development | Done | 5 | Day 4: 5
US010 | T12 | Add confidence score calculation and human-readable reasoning string to Triage Agent output | 18-Jul-2026 | 18-Jul-2026 | Amrutha | Backend Development | Done | 5 | Day 5: 5
US011 | T13 | Design Log Analysis Agent parsing rules for Python, Java, JS/Node and generic log formats | 18-Jul-2026 | 18-Jul-2026 | Amrutha | Design | Done | 3 | Day 6: 3
US011 | T14 | Implement Python traceback parsing (exception type, message, last-frame failure point) | 19-Jul-2026 | 19-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 7: 6
US011 | T15 | Implement Java stack trace and JS/Node runtime error parsing | 20-Jul-2026 | 20-Jul-2026 | Amrutha | Backend Development | Done | 7 | Day 8: 7
US012 | T16 | Extract affected code path(s) list and generate error signature hash for future duplicate detection | 20-Jul-2026 | 20-Jul-2026 | Amrutha | Backend Development | Done | 4 | Day 9: 4
US013 | T17 | Build orchestrator to run Triage Agent and Log Analysis Agent together on every submission | 21-Jul-2026 | 21-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 10: 6
US014 | T18 | Add AgentAnalysis DB model and persist combined structured output keyed by bug_id | 21-Jul-2026 | 21-Jul-2026 | Amrutha | Database Design | Done | 4 | Day 11: 4
US014 | T19 | Wire /api/bugs/paste and /api/bugs/upload to run analysis before save and return it in the response | 22-Jul-2026 | 22-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 12: 6
US014 | T20 | Add GET /api/bugs/{id}/analysis endpoint and update frontend to show agent results in preview and history modal | 22-Jul-2026 | 22-Jul-2026 | Amrutha | Frontend Development | Done | 5 | Day 13: 5
US015 | T21 | Build seeded validation dataset with varied bug report styles and error types | 23-Jul-2026 | 23-Jul-2026 | Amrutha | Testing | Done | 5 | Day 14: 5
US015 | T22 | Write validate_agents.py and run it to measure and report Triage/Log Analysis accuracy | 23-Jul-2026 | 23-Jul-2026 | Amrutha | Testing | Done | 6 | Day 14: 6
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | None | Proceeded as planned with schema design.
1 | 2 | Unsure which fields to index for fast bug lookup. | Added unique index on bug and id columns.
1 | 3 | File upload validation edge cases not fully listed. | Documented full validation rule set before coding.
1 | 4 | Frontend preview regex missed some Java stack trace formats. | Refined regex patterns and retested with sample logs.
1 | 5 | None | Completed testing and closed all logged defects.
2 | 1 |  | Started on Triage Agent keyword rules using the design doc as reference.
2 | 2 | Needed to decide how many keyword matches should count as "strong enough" evidence before bumping severity. | Added a minimum match-count threshold so a single incidental keyword no longer overrides the Medium default.
2 | 3 | Log Analysis Agent regex for JS/Node errors was matching the wrong filename when the stack line had a nested function call. | Tightened the regex to prefer the file:line:col captured inside parentheses first.
2 | 4 | Wiring the orchestrator into the existing paste/upload endpoints without breaking Milestone 1 behavior took longer than estimated. | Ran both agents before creating the DB record and reused the existing severity field instead of adding a new one.
2 | 5 |  | Finished persisting combined agent output and added the /analysis endpoint.
2 | 6 | Frontend history modal did not have a place to show agent results yet. | Added an Agent Analysis section to the modal and preview panel showing severity, confidence bar, and reasoning.
2 | 7 | Needed realistic and varied sample bug reports to test accuracy, not just clean examples. | Built a seeded dataset covering Python, Java, JS, plain-text, and cosmetic/UI reports.
2 | 8 |  | Ran validate_agents.py, reviewed misclassifications, and logged accuracy results for both agents.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 06-Jul-2026 | 10-Jul-2026 | Amrutha | Start reviewing code before merging into the main branch. | Stop skipping input validation during development. | Continue documenting progress and completed tasks. | Added input validation and introduced code review before merging.
2 | 2 | 14-Jul-2026 | 23-Jul-2026 | Amrutha | Start writing small validation scripts alongside each agent instead of testing everything at the end. | Stop hardcoding confidence thresholds without checking them against real varied examples first. | Continue documenting reasoning strings so agent output stays explainable. | Added the seeded validation dataset and adjusted severity/confidence thresholds after reviewing accuracy results.
3
4
5
6
7