## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US001 | As a developer, I want to paste an error/stack trace so it is saved as a bug record. | Must | - | Amrutha | Done
1 | 1 | US002 | As a developer, I want to upload a log/text file as a bug report. | Must Have | US001 | Amrutha | Done
1 | 1 | US003 | As a developer, I want submissions validated (file type, size, empty content) before saving. | Must | US002 | Amrutha | Done
1 | 1 | US004 | As a developer, I want each bug to get a unique, human-readable . | Must | US001 | Amrutha | Done
1 | 1 | US005 | As a developer, I want to see a live preview of the detected error type while typing/uploading. | Should | US001 | Amrutha | Done
2 | 2 | US006 | As a developer, I want to view a history list of all my past bug submissions. | Must | US004 | Amrutha | Done
2 | 2 | US007 | As a developer, I want to open a submission and see its full stored content and metadata. | Must | US006 | Amrutha | Done
2 | 2 | US008 | As a developer, I want to delete a bug submission I no longer need. | Could | US006 | Amrutha | Done
3 | 3 | US016 | As a developer, I would like the system to fetch similar historical defects using the RAG based retrieval in order to be able to propose a hypothesis for the root causes. | Must | US013 | Amrutha | Done
3 | 3 | US017 | I want the Root Cause Agent to produce a level of confidence, and supporting historical evidence, in addition to the hypothesis, as a developer. | Must | US016 | Amrutha | Done
3 | 3 | US018 | As a developer, I wish I had a Duplicate Detection Agent to have scanned past bugs and the history of the KB for any duplicates. | Must | US016 | Amrutha | Done
3 | 3 | US019 | For a developer, there is a need to get the similarity scores and resolution summaries when duplicate matches are present. | Must | US018 | Amrutha | Done
3 | 3 | US020 | As a developer, I want a Remediation Agent to provide me with suggestions for fixes based on previous solutions and root cause analysis. | Must | US019 | Amrutha | Done
3 | 3 | US021 | As a developer, I want remediation suggestions to contain best-practices and confidence scoring. | Should | US020 | Amrutha | Done
3 | 3 | US022 | As a developer, I want to see a Structured Findings Dashboard with all of the above elements in one. | Must | US020 | Amrutha | Done
3 | 3 | US023 | As a developer I would like to populate a historical defect knowledge base for the agents to look up against. | Must | US016 | Amrutha | Done
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 192 | 10 | 12 | 12 | 11 | 12 | 8 | 12 | 7 | 4 | 6 | 4 | 6 | 5 | 11
SPRINT 1 BACKLOG
US001 | T01 | Configure backend framework and dependencies | 06-Jul-2026 | 07-Jul-2026 | Amrutha | Development | Done | 6 | Day 1: 6
US001 | T02 | Design Bug Submission page UI | 07-Jul-2026 | 07-Jul-2026 | Amrutha | UI Design | Done | 5 | Day 2: 5
US001 | T03 | Develop bug report upload API | 07-Jul-2026 | 08-Jul-2026 | Amrutha | Backend Development | Done | 8 | Day 3: 8
US001 | T04 | Implement file validation (extension, size, empty-content checks) | 08-Jul-2026 | 08-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 4: 6
US001 | T05 | Design database schema for bug reports | 08-Jul-2026 | 09-Jul-2026 | Amrutha | Database Design | Done | 7 | Day 5: 7
US001 | T06 | Store uploaded bug reports in database | 09-Jul-2026 | 09-Jul-2026 | Amrutha | Backend Development | Done | 5 | Day 6: 5
US001 | T07 | Implement upload success/error messages | 09-Jul-2026 | 10-Jul-2026 | Amrutha | Frontend Development | Done | 6 | Day 7: 6
US009 | T08 | Design Triage Agent rules: severity keyword sets, weighting logic, and confidence scoring approach | 14-Jul-2026 | 14-Jul-2026 | Amrutha | Design | Done | 4 | Day 1: 4
US009 | T09 | Implement TriageAgent.classify() — severity scoring and Medium default fallback for weak signals | 15-Jul-2026 | 15-Jul-2026 | Amrutha | Backend Development | Done | 7 | Day 2: 7
US009 | T10 | Implement priority mapping (P0-P3) and urgency-keyword priority bump logic | 16-Jul-2026 | 16-Jul-2026 | Amrutha | Backend Development | Done | 4 | Day 3: 4
US009 | T11 | Implement component classification (Auth, Payments, DB, API, Frontend, etc.) via keyword scoring | 17-Jul-2026 | 17-Jul-2026 | Amrutha | Backend Development | Done | 5 | Day 4: 5
US010 | T12 | Add confidence score calculation and human-readable reasoning string to Triage Agent output | 18-Jul-2026 | 18-Jul-2026 | Amrutha | Backend Development | Done | 5 | Day 5: 5
US011 | T13 | Design Log Analysis Agent parsing rules for Python, Java, JS/Node and generic log formats | 18-Jul-2026 | 18-Jul-2026 | Amrutha | Design | Done | 3 | Day 6: 3
US011 | T14 | Implement Python traceback parsing (exception type, message, last-frame failure point) | 19-Jul-2026 | 19-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 7: 6
US011 | T15 | Implement Java stack trace and JS/Node runtime error parsing | 20-Jul-2026 | 20-Jul-2026 | Amrutha | Backend Development | Done | 7 | Day 8: 7
US012 | T16 | Extract affected code path(s) list and generate error signature hash for future duplicate detection | 20-Jul-2026 | 20-Jul-2026 | Amrutha | Backend Development | Done | 4 | Day 9: 4
US013 | T17 | Build orchestrator to run Triage Agent and Log Analysis Agent together on every submission | 21-Jul-2026 | 21-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 10: 6
US014 | T18 | Add AgentAnalysis DB model and persist combined structured output keyed by bug_id | 21-Jul-2026 | 21-Jul-2026 | Amrutha | Database Design | Done | 4 | Day 11: 4
US014 | T19 | Wire /api/bugs/paste and /api/bugs/upload to run analysis before save and return it in the response | 22-Jul-2026 | 22-Jul-2026 | Amrutha | Backend Development | Done | 6 | Day 12: 6
US014 | T20 | Add GET /api/bugs/{id}/analysis endpoint and update frontend to show agent results in preview and history modal | 22-Jul-2026 | 22-Jul-2026 | Amrutha | Frontend Development | Done | 5 | Day 13: 5
US015 | T21 | Build seeded validation dataset with varied bug report styles and error types | 23-Jul-2026 | 23-Jul-2026 | Amrutha | Testing | Done | 5 | Day 14: 5
US015 | T22 | Write validate_agents.py and run it to measure and report Triage/Log Analysis accuracy | 23-Jul-2026 | 23-Jul-2026 | Amrutha | Testing | Done | 6 | Day 14: 6
US016 | T23 | Create a TF-IDF + Cosine Similarity indexer (no external vector DB – all pure Python) | 24-Jul-2026 | 24-Jul-2026 | Amrutha | Backend Development | Done | 6
US023 | T24 | Seed knowledge base table for defectories of representative defects from components | 24-Jul-2026 | 25-Jul-2026 | Amrutha | Database Design | Done | 5
US016 | T25 | Implement RootCauseAgent: get top-k historical matches and create root cause query from Triage + Log Analysis output | 25-Jul-2026 | 25-Jul-2026 | Amrutha | Backend Development | Done | 7
US017 | T26 | Practice with confidence scoring and reasoning string for implementing root cause hypothesis synthesis | 25-Jul-2026 | 26-Jul-2026 | Amrutha | Backend Development | Done | 6
US018 | T27 | Implement DuplicateDetectionAgent: Create Combined Corpus from Historical KB and previous live submissions | 26-Jul-2026 | 26-Jul-2026 | Amrutha | Backend Development | Done | 6
US019 | T28 | Include similarity threshold filtering and resolution summary lookup for duplicate matches. | 26-Jul-2026 | 27-Jul-2026 | Amrutha | Backend Development | Done | 4
US020 | T29 | For RemediationAgent: collect context for Triage/Log/Root Cause/Duplicate and choose best-practice playbook per component | 27-Jul-2026 | 27-Jul-2026 | Amrutha | Backend Development | Done | 7
US021 | T30 | Add remediation grounding sources, confidence blending and step de-duplication logic | 27-Jul-2026 | 28-Jul-2026 | Amrutha | Backend Development | Done | 5
US022 | T31 | To execute all 5 Agents per submission and persist combined AgentAnalysis record, extend Orchestrator to run all 5 agents. | 28-Jul-2026 | 28-Jul-2026 | Amrutha | Backend Development | Done | 6
US022 | T32 | Starts the Structured Findings Dashboard layout | 28-Jul-2026 | 29-Jul-2026 | Amrutha | UI Design | Done | 5
US022 | T33 | Create dashboard rendering of Root Cause evidence cards and Duplicate match cards, using similarity pills. | 29-Jul-2026 | 29-Jul-2026 | Amrutha | Frontend Development | Done | 6
US022 | T34 | Copy the following functions | 29-Jul-2026 | 30-Jul-2026 | Amrutha | Frontend Development | Done | 5
US022 | T35 | To document 5-agent Structured Findings Dashboard | 30-Jul-2026 | 31-Jul-2026 | Amrutha | Frontend Development | Done | 4
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | None | Proceeded as planned with schema design.
1 | 2 | Unsure which fields to index for fast bug lookup. | Added unique index on bug and id columns.
1 | 3 | File upload validation edge cases not fully listed. | Documented full validation rule set before coding.
1 | 4 | Frontend preview regex missed some Java stack trace formats. | Refined regex patterns and retested with sample logs.
1 | 5 | None | Completed testing and closed all logged defects.
2 | 1 |  | Started on Triage Agent keyword rules using the design doc as reference.
2 | 2 | Needed to decide how many keyword matches should count as "strong enough" evidence before bumping severity. | Added a minimum match-count threshold so a single incidental keyword no longer overrides the Medium default.
2 | 3 | Log Analysis Agent regex for JS/Node errors was matching the wrong filename when the stack line had a nested function call. | Tightened the regex to prefer the file:line:col captured inside parentheses first.
2 | 4 | Wiring the orchestrator into the existing paste/upload endpoints without breaking Milestone 1 behavior took longer than estimated. | Ran both agents before creating the DB record and reused the existing severity field instead of adding a new one.
2 | 5 |  | Finished persisting combined agent output and added the /analysis endpoint.
2 | 6 | Frontend history modal did not have a place to show agent results yet. | Added an Agent Analysis section to the modal and preview panel showing severity, confidence bar, and reasoning.
2 | 7 | Needed realistic and varied sample bug reports to test accuracy, not just clean examples. | Built a seeded dataset covering Python, Java, JS, plain-text, and cosmetic/UI reports.
2 | 8 |  | Ran validate_agents.py, reviewed misclassifications, and logged accuracy results for both agents.
3 | 1 |  | Started building the TF-IDF similarity utility and seeding the historical defect KB.
3 | 2 | Unclear how many top-k matches to retrieve for a useful but not noisy root cause hypothesis. | Settled on top-3 matches with strong/weak similarity thresholds (0.35 / 0.15).
3 | 3 | Duplicate Detection Agent was returning too many low-similarity noise matches from short bug titles. | Added a 0.20 similarity threshold to filter out weak duplicate candidates.
3 | 4 | Remediation Agent recommendations sometimes repeated the same step from both duplicate and root cause context. | Added step de-duplication while preserving priority order.
3 | 5 | Needed a consistent way to trace which recommendations came from historical data vs best-practice rules. | Added a sources list to Remediation output recording every grounding reference.
3 | 6 |  | Finished the Orchestrator changes to run all 5 agents and persist one combined AgentAnalysis record.
3 | 7 | Dashboard was becoming cluttered trying to show 5 agent sections on one panel. | Split the dashboard into clearly separated, color-coded sections per agent with confidence bars.
3 | 8 |  | Completed dashboard wiring for both the live preview and the history detail modal.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 06-Jul-2026 | 10-Jul-2026 | Amrutha | Start reviewing code before merging into the main branch. | Stop skipping input validation during development. | Continue documenting progress and completed tasks. | Added input validation and introduced code review before merging.
2 | 2 | 14-Jul-2026 | 23-Jul-2026 | Amrutha | Start writing small validation scripts alongside each agent instead of testing everything at the end. | Stop hardcoding confidence thresholds without checking them against real varied examples first. | Continue documenting reasoning strings so agent output stays explainable. | Added the seeded validation dataset and adjusted severity/confidence thresholds after reviewing accuracy results.
3 | 3 | 24-Jul-2026 | 2026-08-31 | Amrutha |  | Start designing similarity thresholds against sample data before hardcoding them into agents. | Continue tracing every recommendation back to its grounding source for explainability. | Tuned similarity thresholds against real seeded data and standardized dashboard section styling across all 5 agents.
4
5
6
7